## 2 - Project Plan
% Complete | Status | RAG | Type | Task Name | Predecessors | Duration | Start | Finish | Assigned To | Latest comment
KPIs
|  | Green | KPI | Budget - Within Budget
|  | Green | KPI | Schedule - On Time
|  | Green | KPI | Scope - In Scope
|  | Green | KPI | Risk - Nothing at risk
|  | Green | KPI | Resources - Aligned
6% | In Progress | Green | Project Summary | RTG - WebEx Contact Center & WebEx Calling |  | 155d | 2023-08-07 | 2024-03-15
100% | Not Started | Green | Phase | 1.0 Project Initiation |  | 4d | 2023-08-07 | 2023-08-10
100% | In Progress |  |  | 1.1 Project Asset Creation/Scope Review |  | 1d | 2023-08-07 | 2023-08-07
100% | In Progress |  |  | 1.2 Internal Kick-Offs |  | 1d | 2023-08-10 | 2023-08-10
100% | In Progress |  |  | 1.3 Project Kick-Off |  | 1d | 2023-08-10 | 2023-08-10
8% | In Progress | Green | Phase | 2.0 PSTN Strategy |  | 25d | 2023-08-11 | 2023-09-15
100% | Complete |  |  | 2.1 Review/verify firewall and security requirements with Client |  | 5d | 2023-08-11 | 2023-08-17
0% | Not Started |  |  | 2.2 Configure Single Sign On integration with WebEx calling |  | 5d | 2023-09-11 | 2023-09-15
0% | Not Started |  |  | 2.3 Deploy WebEx Directory Connector for user import |  | 5d | 2023-09-11 | 2023-09-15
0% | Not Started |  |  | 2.4 Configure approximately 180 locations in WebEx Calling |  | 5d | 2023-09-11 | 2023-09-15
0% | Not Started |  |  | 2.5 Configure RedSky E911 for WebEx Calling |  | 5d | 2023-09-11 | 2023-09-15
0% | Not Started |  |  | 2.5.1 RedSky will be utilized for softphone users. |  | 5d | 2023-09-11 | 2023-09-15
0% | Not Started |  |  | 2.6 Import phones for locations and prepare for Client migration |  | 5d | 2023-09-11 | 2023-09-15
0% | Not Started |  |  | 2.7 Store phones will be configured in a Key System design using a single user for all shared phones. |  | 5d | 2023-09-11 | 2023-09-15
0% | Not Started |  |  | 2.7.1 The first line included the DID for the store. |  | 5d | 2023-09-11 | 2023-09-15
0% | Not Started |  |  | 2.7.2 Virtual lines will be used for rollover line on the phone for ease of answering. |  | 5d | 2023-09-11 | 2023-09-15
0% | Not Started |  |  | 2.7.3 The first line will be used for all outbound calls. |  | 5d | 2023-09-11 | 2023-09-15
0% | Not Started |  |  | 2.8 Configure auto attendant for each location |  | 5d | 2023-09-11 | 2023-09-15
0% | Not Started |  |  | 2.9 Configure PSTN Integration |  | 5d | 2023-09-11 | 2023-09-15
0% | Not Started |  |  | 2.10 Integration with WebEx Contact Center team |  | 5d | 2023-09-11 | 2023-09-15
0% | Not Started |  |  | 2.11 General WebEx Calling configurations |  | 5d | 2023-09-11 | 2023-09-15
0% | Not Started |  |  | 2.12 Obtain approval for migration and establish migration schedule with Client |  | 5d | 2023-09-11 | 2023-09-15
33% | In Progress | Green | Phase | 3.0 Project Discovery and Order - Contact Center |  | 10d | 2023-08-21 | 2023-09-01
100% | Complete |  |  | 3.1 Discovery Workshop 1 – Existing flow review, Client education and best practice review, high level flow design |  | 10d | 2023-08-21 | 2023-09-01
100% | Complete |  |  | 3.2 Discovery Workshop 2 – Client-specific design begins, call type review and design, develop functional specification |  | 10d | 2023-08-21 | 2023-09-01
0% | Not Started |  |  | 3.3 Approval of call flows |  | 10d | 2023-08-21 | 2023-09-01
0% | Not Started |  |  | 3.4 Baseline Deployment |  | 10d | 2023-08-21 | 2023-09-01
0% | Not Started |  |  | 3.5 Review configuration and performance |  | 10d | 2023-08-21 | 2023-09-01
0% | Not Started |  |  | 3.6 Evaluate minor changes and implement (using Support Block) |  | 10d | 2023-08-21 | 2023-09-01
10% | In Progress |  | Phase | 4.0 Project Discovery - WebEx Calling |  | 14d | 2023-08-21 | 2023-09-08
100% | Complete |  |  | 4.1 Existing network Discovery |  | 5d | 2023-08-21 | 2023-08-25
0% | Not Started |  |  | 4.2 Site Definitions and Types |  | 9d | 2023-08-28 | 2023-09-08
0% | Not Started |  |  | 4.3 Naming Conventions |  | 9d | 2023-08-28 | 2023-09-08
0% | Not Started |  |  | 4.4 Determine Virtual Space |  | 9d | 2023-08-28 | 2023-09-08
0% | Not Started |  |  | 4.5 Call Flow approval |  | 9d | 2023-08-28 | 2023-09-08
0% | Not Started |  |  | 4.6 Soft Phone Requirements |  | 9d | 2023-08-28 | 2023-09-08
16% | In Progress | Green | Phase | 5.0 A2Q and Provisioning |  | 10d | 2023-08-28 | 2023-09-11
80% | In Progress |  |  | 5.1 Submit A2Q form |  | 10d | 2023-08-28 | 2023-09-11
0% | Not Started |  |  | 5.2 Cisco Approval |  | 10d | 2023-08-28 | 2023-09-11
0% | Not Started |  |  | 5.3 CTP to approve release of order |  | 10d | 2023-08-28 | 2023-09-11
0% | Not Started |  |  | 5.4 Key contacte listed on the order will receive the provisioning email |  | 10d | 2023-08-28 | 2023-09-11
0% | Not Started |  |  | 5.5 Complete Provisioning |  | 10d | 2023-08-28 | 2023-09-11
0% | Not Started | Green | Phase | 6.0 Design | 43 | 20d | 2023-09-12 | 2023-10-09
0% | Not Started |  |  | 6.1 Create and document system design |  | 20d | 2023-09-12 | 2023-10-09
0% | Not Started |  |  | 6.1.1 Feature requirements |  | 20d | 2023-09-12 | 2023-10-09
0% | Not Started |  |  | 6.1.2 Integration with WebEx Contact Center team |  | 20d | 2023-09-12 | 2023-10-09
0% | Not Started |  |  | 6.1.3 Location Listing |  | 20d | 2023-09-12 | 2023-10-09
0% | Not Started |  |  | 6.1.4 Directory Integration |  | 20d | 2023-09-12 | 2023-10-09
0% | Not Started |  |  | 6.1.5 Dial Plan |  | 20d | 2023-09-12 | 2023-10-09
0% | Not Started |  |  | 6.1.6 E911 |  | 20d | 2023-09-12 | 2023-10-09
0% | Not Started |  |  | 6.2 Verify Software and Licenses/Provisioning |  | 20d | 2023-09-12 | 2023-10-09
0% | Not Started |  |  | 6.3 Develop Test Plan |  | 20d | 2023-09-12 | 2023-10-09
0% | Not Started |  |  | 6.4 Cutover/DID migration strategy |  | 20d | 2023-09-12 | 2023-10-09
0% | Not Started | Green | Phase | 7.0 Configuration | 49 | 30d | 2023-10-10 | 2023-11-20
0% | Not Started |  |  | 7.1 Programming |  | 30d | 2023-10-10 | 2023-11-20
0% | Not Started |  |  | 7.2 Develop call routing scripts based upon functional design document |  | 30d | 2023-10-10 | 2023-11-20
0% | Not Started | Green | Phase | 8.0 Testing and UAT | 60 | 20d | 2023-11-21 | 2023-12-20
0% | Not Started |  |  | 8.1 Test all routing scenarios per Call Flow |  | 20d | 2023-11-21 | 2023-12-20
0% | Not Started |  |  | 8.2 Test overflow conditions |  | 20d | 2023-11-21 | 2023-12-20
0% | Not Started |  |  | 8.3 Test Skills based routing |  | 20d | 2023-11-21 | 2023-12-20
0% | Not Started |  |  | 8.4 Test TOD/DOW routing |  | 20d | 2023-11-21 | 2023-12-20
0% | Not Started |  |  | 8.5 Test Holiday routing |  | 20d | 2023-11-21 | 2023-12-20
0% | Not Started |  |  | 8.6 Test Voicemail hand-off |  | 20d | 2023-11-21 | 2023-12-20
0% | Not Started |  |  | 8.7 Test Emergency closed call routing |  | 20d | 2023-11-21 | 2023-12-20
0% | Not Started |  |  | 8.8 Testing of Calabrio |  | 20d | 2023-11-21 | 2023-12-20
0% | Not Started |  |  | 8.9 Integration with WebEx Contact Center team |  | 20d | 2023-11-21 | 2023-12-20
0% | Not Started | Green | Phase | 9.0 Pre-Cutover Adjustments | 63 | 10d | 2023-12-21 | 2024-01-05
0% | Not Started |  |  | 9.1 Make necessary adjustments to design |  | 10d | 2023-12-21 | 2024-01-05
0% | Not Started |  |  | 9.2 Testing and validation |  | 10d | 2023-12-21 | 2024-01-05
0% | Not Started | Green | Phase | 10.0 Training | 73 | 5d | 2024-01-08 | 2024-01-12
0% | Not Started |  |  | 10.1 Familiarization training for support staff |  | 5d | 2024-01-08 | 2024-01-12
0% | Not Started |  |  | 10.2 Handoff to Converge Managed Services |  | 5d | 2024-01-08 | 2024-01-12
0% | Not Started |  |  | 10.3 Finalize documentation and system turnover |  | 5d | 2024-01-08 | 2024-01-12
0% | Not Started |  |  | 10.4 WebEx CC Supervisor and Agent training |  | 5d | 2024-01-08 | 2024-01-12
0% | Not Started |  |  | 10.5 CUIC historical reporting overview |  | 5d | 2024-01-08 | 2024-01-12
0% | Not Started |  |  | 10.6 Real time reporting Overview |  | 5d | 2024-01-08 | 2024-01-12
0% | Not Started | Green | Phase | 11.0 Cutover/Go Live | 76 | 40d | 2024-01-15 | 2024-03-08
0% | Not Started |  |  | 11.1 Update Local gateway to send appropriate DIDs to WebEx Calling |  | 40d | 2024-01-15 | 2024-03-08
0% | Not Started |  |  | 11.2 Migration details will be documented as part of planning and design. |  | 40d | 2024-01-15 | 2024-03-08
0% | Not Started | Green | Phase | 12.0 Project Close | 83 | 5d | 2024-03-11 | 2024-03-15
0% | Not Started |  |  | 12.1 Finalize documentation deliverables |  | 5d | 2024-03-11 | 2024-03-15
0% | Not Started |  |  | 12.1.1 Project Plan |  | 5d | 2024-03-11 | 2024-03-15
0% | Not Started |  |  | 12.1.2 System Design Document |  | 5d | 2024-03-11 | 2024-03-15
0% | Not Started |  |  | 12.1.3 Test Plan |  | 5d | 2024-03-11 | 2024-03-15
0% | Not Started |  |  | 12.1.4 Migration Plan |  | 5d | 2024-03-11 | 2024-03-15
0% | Not Started |  |  | 12.1.5 End user training document |  | 5d | 2024-03-11 | 2024-03-15
0% | Not Started |  |  | 12.2 Project closeout meeting |  | 5d | 2024-03-11 | 2024-03-15
0% | Not Started |  |  | 12.2.1 Formally acknowledge all project scope items have been completed |  | 5d | 2024-03-11 | 2024-03-15

## Summary
Not Started | 67
In Progress | 4
On Hold | 0
Complete | 4